Discovery and Scoping Strategy Review

Assignment context:** A company wants to deploy AI across customer

support, operations, compliance, and internal knowledge management.

Leadership believes AI will improve productivity but has not defined

priorities. This repository designs the discovery and scoping *strategy*

— the process for reaching a defensible, evidence-based first-domain

selection — rather than picking a domain outright before any discovery

has happened.

Read this first

[`REVIEW.md`](REVIEW.md)** — the core 2-page review document, covering all seven required sections: Stakeholder Analysis, Discovery Plan, Interview Strategy, Requirement Prioritization, Success Metrics, Risk Assessment, and Exit Criteria.

Supporting analysis

The review document is intentionally concise; these files hold the

detail behind it:

| File | Contents |

| [`supporting-analysis/stakeholder-analysis.md`](supporting-analysis/stakeholder-analysis.md) | Full power-interest grid across all four domains, with per-domain stakeholder detail |

| [`supporting-analysis/interview-question-bank.md`](supporting-analysis/interview-question-bank.md) | Complete interview scripts for Executives, Managers, End Users, and Technical Teams |

| [`supporting-analysis/prioritization-backlog.md`](supporting-analysis/prioritization-backlog.md) | The domain-scoring model, illustrative Must/Should/Could-have backlog, and the full risk register with likelihood/impact ratings |

Core idea running through this review

With four candidate domains and no pre-defined priority, the central risk isn't picking the *wrong* domain — it's picking *any* domain before evidence exists to justify it. Every section of this review is built around one discipline: interview broadly across all four domains first,

score candidates on value/measurability/feasibility, and only then scope narrowly into one — while keeping the other three domains documented and sequenced, not discarded.

# Discovery and Scoping Strategy Review

### AI Deployment Across Customer Support, Operations, Compliance & Knowledge Management

**Context:** Leadership believes AI will improve productivity across four

domains but has not defined priorities. This review designs the

discovery and scoping strategy needed before any build begins — not a

recommendation for which domain to build in first, but the *process*

for reaching that decision defensibly. Deeper detail behind each section

lives in [`supporting-analysis/`](supporting-analysis/).

---

## 1. Stakeholder Analysis

| Group | Priority | Power / Interest |

|---|---|---|

| **Executives (Sponsor)** | A board-reportable productivity win, fast | High power / variable interest — often high initially, drops once delivery takes longer than a demo |

| **Department Managers** (Support, Ops, Compliance, Knowledge Mgmt) | Solve *their* team's specific pain, resist scope that doesn't serve it | High power over their domain / high interest |

| **End Users** (agents, analysts, ops staff) | Tools that reduce their actual daily friction, not add oversight | Low formal power / highest interest — best source of real requirements and workarounds |

| **Technical Teams (IT/Security/Data)** | Feasibility, access control, no new attack surface | High power to block / often low interest until asked |

| **Compliance/Legal** | No new regulatory exposure, auditability | High power to block, especially in this engagement given the compliance domain is explicitly in scope / interest scales with how close a candidate project sits to regulated data |

Four domains means four sets of department priorities competing for the

same discovery time and the same initial build slot — this tension is

the central risk this strategy is designed to manage (see §6).

Full grid: [`supporting-analysis/stakeholder-analysis.md`](supporting-analysis/stakeholder-analysis.md).

## 2. Discovery Plan (First Four Weeks)

| Week | Focus |

|---|---|

| **0** | Stakeholder mapping across all four domains; agree on an evaluation-vs-build split; confirm no domain is pre-selected by leadership before discovery completes |

| **1–2** | Structured interviews and workflow observation in *all four* domains in parallel (shallow-but-broad), not deep in one — premature depth in one domain before comparison risks anchoring on whichever team was interviewed first |

| **3** | Cross-domain bottleneck comparison: score each domain's candidate problems against value, measurability, and feasibility (see §4); narrow to one scoped bottleneck |

| **4** | Co-design success metrics and evaluation approach with the selected domain's stakeholders; validate requirements; draft the scope document and engagement contract |

Discovery does not end at week four — it continues through feedback

loops post-deployment, and the three unselected domains remain

documented candidates for the next engagement cycle rather than

abandoned.

## 3. Interview Strategy

Open-ended, workflow-first questions, not yes/no checklists — see the

full question bank in

[`supporting-analysis/interview-question-bank.md`](supporting-analysis/interview-question-bank.md).

Representative questions by group:

- **Executives:** "What does success look like in board terms? What

would make this initiative a failure even if the tool works

technically?"

- **Managers:** "Walk me through your team's week. Where do things

break or get stuck?"

- **End Users:** "What's the most annoying five-minute task you do

every day? What workaround have you built that nobody else knows

about?"

- **Technical Teams:** "What access, data, or compliance constraints

would block this before it even starts?"

## 4. Requirement Prioritization

| Bucket | Examples surfaced across the four domains |

|---|---|

| **Must have** | One scoped, measurable bottleneck from whichever domain scores highest on value × measurability × feasibility; an evaluation dataset seeded from real historical examples; explicit constraints from IT/Compliance honored from day one |

| **Should have** | Cross-domain reusability of any retrieval/knowledge component (e.g., a knowledge-management improvement may quietly benefit support); a rationale/audit trail for any compliance-adjacent output |

| **Could have** | Expansion into the other three domains as separate, later-scoped engagements; shared infrastructure (e.g., a common knowledge base) built once requirements from two domains converge naturally |

Full backlog with scoring rationale:

[`supporting-analysis/prioritization-backlog.md`](supporting-analysis/prioritization-backlog.md).

## 5. Success Metrics

Metrics are defined *after* domain selection, not before — a

cross-domain metric agreed in the abstract ("improve productivity 20%")

invites exactly the vague-goal failure discovery is meant to prevent.

The discovery plan instead commits to a **process**:

- Every candidate bottleneck gets one time, one cost/error, and one

satisfaction metric, specific and time-bound, before it's eligible

for selection in week 3.

- The selected domain's metrics are co-designed with its stakeholders

in week 4, paired one-to-one with an evaluation method (the

eval-customer split), not decided unilaterally by the delivery team.

## 6. Risk Assessment

| Risk | From | Mitigation |

|---|---|---|

| **Executive picks a domain before discovery finishes**, based on the loudest request rather than evidence | Poor scoping | Week-0 agreement that domain selection happens in week 3, based on the scoring model, not on pre-discovery preference |

| **Four domains dilute interview time**, producing shallow findings everywhere | Poor discovery | Weeks 1–2 explicitly scoped as shallow-but-broad, with depth reserved for the selected domain in later weeks |

| **Compliance risk surfaces only after a domain is already selected** (e.g., a chosen support/knowledge-management tool touches regulated data) | Poor discovery | Compliance/Legal interviewed in week 1 across *all* domains, not only the winning one, specifically to catch this before selection |

| **Scope creep after a successful pilot** in the selected domain (other departments asking "can it also...") | Poor scoping | Engagement contract and must/should/could-have list established in week 4, with a documented change-management process for new requests |

| **No shared definition of "done"** turns a scoped pilot into indefinite expansion across all four domains | Poor scoping | Exit criteria (§7) defined before build begins, tied to the single selected domain only |

Full risk register with likelihood/impact:

[`supporting-analysis/prioritization-backlog.md`](supporting-analysis/prioritization-backlog.md#risk-register).

## 7. Exit Criteria

The discovery-and-scoping engagement (not the eventual build) is

complete when:

- [ ] All four domains have been interviewed at the shallow-but-broad

level (week 1–2 standard met for each).

- [ ] One bottleneck is selected via the documented scoring model, with

the selection rationale recorded and shared with all four

department managers — including the three not selected, so their

input is visibly acknowledged rather than silently dropped.

- [ ] A scope document, success metrics, eval-customer split, and

engagement contract exist for the selected domain and are signed

off by its stakeholders, IT/Security, and the executive sponsor.

- [ ] A documented, time-stamped backlog of the three deferred domains

exists for future engagement planning — discovery findings are

not discarded, only sequenced.

Meeting these criteria hands off a scoped, evidence-based build

engagement — it does not itself constitute the AI deployment.

# Supporting Analysis: Requirement Prioritization & Risk Register

## Domain scoring model (used in Week 3 to select one bottleneck)

Each candidate bottleneck, once identified within a domain, is scored

1–5 on three axes. This is the mechanism referenced in `REVIEW.md` §4 —

it exists specifically so domain selection is defensible evidence, not

whichever executive or manager spoke most persuasively.

| Axis | Definition | Example scoring question |

|---|---|---|

| **Value** | Time, cost, error, or satisfaction impact if solved | How many hours/dollars/errors does this bottleneck cost per month? |

| **Measurability** | Can success be verified against real historical data? | Does labeled or reconstructable historical data already exist? |

| **Feasibility** | Compatible with IT/Security/Compliance constraints surfaced in week 1? | Does the likely solution shape require new data storage, write access, or regulated-data handling? |

A domain's top candidate bottleneck advances only if it scores at

least 3/5 on all three axes — a high-value but low-feasibility

candidate (e.g., something requiring write access to a regulated

system) is documented but not selected for the first engagement.

## Illustrative backlog (populated with representative candidates —

final version depends on actual week 1–2 findings)

### Must have

| Item | Domain | Rationale |

|---|---|---|

| One scoped, measurable bottleneck selected via the scoring model | Whichever domain wins | This is the single non-negotiable output of discovery |

| Evaluation dataset seeded from real historical examples in the selected domain | Selected domain | Prevents shipping against synthetic-only, "too clean" test cases |

| IT/Security and Compliance constraints honored in the initial design | All (checked across all four in week 1) | A constraint discovered after build begins is far costlier than one discovered during discovery |

| Engagement contract with defined exit criteria | Selected domain | Prevents "no one defined done" turning a pilot into indefinite maintenance |

### Should have

| Item | Domain | Rationale |

|---|---|---|

| Rationale/audit trail on AI output | Compliance-adjacent domains especially, but valuable everywhere per end-user trust findings | Directly addresses the "how would you know to trust it" interview finding |

| Reusable retrieval/knowledge component | Knowledge Management, but shareable with Support | A knowledge-base improvement in one domain often has direct reuse value in another — should be evaluated once the selected domain is known |

| New-hire ramp-time tracking | Support, Operations | Secondary evidence of whether the tool reduces institutional-knowledge dependency, not just speeds up an existing expert |

### Could have (explicitly deferred, not rejected)

| Item | Domain | Rationale for deferral |

|---|---|---|

| Expansion into the three non-selected domains | All | Sequenced as future engagements once the first is proven — see Exit Criteria in `REVIEW.md` §7 |

| Shared infrastructure across domains (e.g., one knowledge base serving both Support and Knowledge Management) | Cross-domain | Premature to build shared infrastructure before any single domain's requirements are validated |

| Any regulated-filing or legal-output generation | Compliance | Requires a dedicated compliance review before even entering discovery scope, per General Counsel's high-power position |

---

## Risk Register

Expanded version of `REVIEW.md` §6, with likelihood and impact scored

Low/Medium/High.

| Risk | Source | Likelihood | Impact | Mitigation |

|---|---|---|---|---|

| Executive pre-selects a domain based on preference, not evidence | Poor scoping | Medium | High | Week-0 agreement that selection happens in week 3 via the scoring model; documented explicitly in the engagement contract |

| Shallow findings from splitting interview time across four domains | Poor discovery | Medium | Medium | Weeks 1–2 are explicitly shallow-but-broad by design, not an accidental compromise; depth is reserved for the selected domain from week 3 onward |

| Compliance/legal risk surfaces after domain selection | Poor discovery | Low-Medium | High | Compliance and Legal interviewed in week 1 across all four domains specifically to catch this before, not after, selection |

| Scope creep after early pilot success in the selected domain | Poor scoping | Medium-High | Medium | Must/should/could-have list and change-management process established in week 4, before build begins |

| No shared definition of "done" | Poor scoping | Medium | High | Exit criteria defined in week 4, tied only to the selected domain, before build begins |

| Deferred domains perceived as "rejected" rather than "sequenced," damaging stakeholder trust for future engagements | Poor discovery communication | Medium | Medium | Selection rationale explicitly shared with all four department managers, not only the winning one, per `REVIEW.md` §7 exit criteria |

| Access-provisioning lead time (IT/Security) not accounted for in the build timeline | Poor scoping | Low-Medium | Medium | Access requests for the selected domain submitted at week 4/engagement kickoff, not after build begins |

# Supporting Analysis: Stakeholder Analysis

Full power-interest grid across all four candidate domains

(Customer Support, Operations, Compliance, Internal Knowledge

Management). The summary table in `REVIEW.md` §1 condenses this; this

document preserves the per-domain detail needed to actually run the

week-1 interviews.

## High power, high interest

| Stakeholder | Domain(s) | Priority | Definition of success | Concern |

|---|---|---|---|---|

| Executive Sponsor | All | Board-reportable win within a defined window | A measurable metric, not a demo | Discovery taking "too long" before visible progress |

| Support Operations Manager | Customer Support | Reduce ticket volume/time without hurting CSAT | Faster resolution, stable or better satisfaction scores | A tool that looks fast but increases wrong answers or escalations |

| Operations Director | Operations | Reduce manual process time, fewer errors | Time and error reduction, verifiable against current baselines | Being asked to change process before the AI is proven |

| Compliance Officer | Compliance | No new regulatory exposure; ideally, less manual audit burden | Full auditability of any AI-assisted decision | AI making or influencing compliance decisions without a human-reviewable trail |

| Knowledge Management Lead | Internal Knowledge Mgmt | Reduce time employees spend searching for information | Measurable drop in "I can't find X" complaints/tickets | A tool that returns confidently wrong answers from stale documents |

## High power, low interest (until engaged directly)

| Stakeholder | Domain(s) | Priority | Definition of success | Concern |

|---|---|---|---|---|

| VP of IT/Security | All | No new attack surface; controlled access | Read-only or scoped access, standard approval workflow followed | Being asked for access after a project is already underway |

| General Counsel | Compliance (primarily), but relevant wherever regulated data may appear | No engagement creates legal exposure | Explicit compliance sign-off before any regulated-data-adjacent build | Scope quietly expanding into legal-adjacent territory without review |

| CFO/Finance leadership | All (cost owner) | ROI clarity before broad investment | A believable cost-benefit case from the first scoped pilot | Four domains turning into four simultaneous budgets |

## Low power, high interest

| Stakeholder | Domain(s) | Priority | Definition of success | Concern |

|---|---|---|---|---|

| Support agents | Customer Support | Less time on repetitive lookup/cross-referencing | The tool saves time on the task they find most tedious | A tool designed without asking them first |

| Operations/process staff | Operations | Fewer manual steps, less error-prone handoffs | Process actually gets easier, not just "monitored more" | Increased oversight framed as "help" |

| Compliance analysts | Compliance | Less manual document review/checking | Faster review without losing defensibility | Being blamed if an AI-assisted review misses something |

| General employees | Internal Knowledge Mgmt | Find answers without asking a person or searching five systems | Fast, trustworthy answers to common internal questions | A search tool that's confidently wrong |

## Low power, low interest

| Stakeholder | Domain(s) | Priority | Concern |

|---|---|---|---|

| Adjacent departments not yet targeted | All | Curious, informally requesting "can it also do X" | Being told "not yet" — low risk given low interest, but a common source of scope-creep requests (see Risk Assessment) |

## How this grid shapes the discovery plan

- **End users across all four domains are interviewed in weeks 1–2**

specifically because they are consistently the highest-interest,

lowest-power group — exactly the population whose findings are most

likely to be overridden by louder executive or manager voices if not

captured directly and early.

- **IT/Security and Legal are interviewed in week 1 across all four

domains**, not only the eventually-selected one, because their

high-power/low-interest position means they will not proactively

raise a blocking constraint unless asked — and a constraint discovered

after domain selection is far more costly than one discovered before.

- **Executive sponsorship is treated as a high-power/variable-interest

relationship** — sustained specifically through the discovery plan's

weekly cadence (README §2), because sponsor interest measurably drops

once initial excitement fades and delivery takes longer than a demo.